## POC Schedule
Task | Description | Dependencies | Output | Priority | Responsibility | Start Time | End Time
POC Scope Finalization | Define objective, use cases, app list, and timeframe for POC. | None | POC plan | High | Architect / Lead
Environment Setup | Set up minimal infra (Prometheus, AppD, Splunk access; test cluster) | POC plan | Working test environment | High | DevOps / SRE
Data Collection Scripts | Scripts to fetch metrics/logs for 2-3 apps over 2-3 days. | Environment Setup | Collected data files | High | SRE
Model Training (Manual) | Run offline training of anomaly, ranking, prediction models using limited dataset. | Data Collection | Trained model files | High | ML Engineer
Model Store Setup | Store trained models in filesystem or S3-style bucket. | Model Training | Saved models (.pkl/.h5) | Medium | ML Engineer
FastAPI + LangChain Setup | Create basic FastAPI server with agentic logic routing via LangChain tools. | Environment Setup | Running backend API | High | Backend Engineer
Anomaly Detection Agent | Load model and expose anomaly detection endpoint. | Model Store Setup | Anomaly detection agent | High | ML Engineer / Backend
Suspect Ranking Agent | Expose rule or ML based RCA endpoint for known apps. | Model Store Setup | Suspect ranking endpoint | Medium | ML Engineer
Forecast Agent | Expose forecasting for select metrics using pre-trained model. | Model Store Setup | Forecast endpoint | Medium | ML Engineer
Chatbot UI (Simple) | Implement minimal web UI or Streamlit interface for user query input. | FastAPI Setup | Working chatbot UI | Medium | Frontend Dev
End-to-End Flow Test | Test flow: chatbot → FastAPI → agent → model → response | All agents + UI | Validated POC loop | High | Full Team
Demo Preparation | Prepare use case walkthrough, slides, and validation report. | Successful E2E test | POC demo deck | High | All

## Full Schedule
Agentic Observability System Development Schedule
Task | Description | Dependencies | Output | Priority | Responsibility | Start Time | End Time
Architecture Review & Planning | Review the proposed multi-agent architecture, finalize design decisions for each component, and create a detailed implementation plan. Establish the scope and resource allocation for the project. | None | Architecture design document and project plan with defined milestones. | High | Solution Architect / Team Lead
Infrastructure & Environment Setup | Provision and configure the base infrastructure (servers, Kubernetes/OpenShift cluster, etc.) for the observability system. Ensure all required services (e.g., databases, message brokers) are available and connectivity to data sources is established. | Architecture plan finalized (Task: Architecture Review & Planning). | Development & test environment ready with necessary platforms installed (e.g., cluster up, network configured). | High | DevOps Engineer / SRE
CI/CD Pipeline Setup | Establish a continuous integration and deployment pipeline. Set up code repositories, automated build/test workflows, and deployment scripts to streamline development and ensure consistent releases. | Architecture plan finalized; Development environment (infrastructure) in place. | CI/CD pipeline configured (e.g., GitHub Actions or Jenkins pipelines) with automated testing and deployment capabilities. | Medium | DevOps Engineer
Prometheus Data Integration | Develop connectors or services to ingest metrics from Prometheus. Ensure the system can query Prometheus’s APIs or scrape data on schedule, and transform it into a format suitable for analysis/storage. | Infrastructure setup complete; Access to Prometheus instance. | Prometheus metrics ingestion module delivering metric data into the central pipeline. | High | SRE / Observability Engineer
AppDynamics Data Integration | Connect to AppDynamics APIs to retrieve application performance metrics and events. Build integration that regularly pulls relevant data and feeds it into the observability data pipeline. | Infrastructure setup complete; AppDynamics credentials and API access available. | AppDynamics data ingestion module providing application performance data to the central pipeline. | Medium | SRE / Observability Engineer
Splunk Data Integration | Implement integration with Splunk for log data. Set up queries or use Splunk’s API to fetch relevant logs and events, then parse and ingest them into the central observability data store. | Infrastructure setup complete; Splunk access (credentials, endpoint) available. | Log ingestion module that pulls and stores log data from Splunk into the system. | High | SRE / Observability Engineer
OpenShift API Integration | Integrate with the OpenShift cluster API to collect cluster and application state data (resource usage, events). Develop scripts/services to fetch this data, enabling the system to use it for context and automation. | Infrastructure setup complete; Access to OpenShift cluster API (credentials). | OpenShift data ingestion module providing cluster state and events data into the system. | Medium | DevOps Engineer / SRE
Central Data Pipeline & Storage Setup | Create a unified data pipeline that aggregates metrics and logs from all sources (Prometheus, AppDynamics, Splunk, OpenShift). Set up a storage solution (database or data lake) with a defined schema for storing and querying the integrated observability data. | Data source integrations completed (Prometheus, AppDynamics, Splunk, OpenShift data available). | Central repository of observability data (with schema) and data pipeline jobs that populate it with integrated data. | High | Data Engineer / SRE
Dagster Orchestration Setup | Install and configure Dagster for orchestrating data processing and model training workflows. Initialize a Dagster project and ensure it can schedule and run jobs for data analysis and model pipeline execution. | Infrastructure ready for deployment; Central data pipeline in place for data access. | Dagster instance running and able to execute pipeline jobs (initial Dagster skeleton established). | High | ML Engineer / Data Engineer
Celery Background Job Setup | Set up Celery workers for asynchronous task processing (with a message broker like RabbitMQ/Redis). Configure Celery within the project to handle long-running tasks such as model training without blocking the system. | Infrastructure ready (message broker provisioned); Dagster or base project structure set up. | Operational Celery worker system (with broker) ready to execute background tasks on-demand. | High | DevOps Engineer / Backend Engineer
Develop Anomaly Detection Model | Design and implement the anomaly detection algorithm. Use historical metrics data to develop a machine learning or statistical model that can identify abnormal patterns or outliers in Prometheus/AppDynamics metrics. | Prometheus & AppDynamics data available (historical); Central data storage in place for training data. | Anomaly detection model code and initial trained model (ready to detect metric anomalies). | High | Data Scientist / ML Engineer
Develop Suspect Ranking Model | Develop the root cause analysis model to rank likely suspect components or services when an anomaly is detected. Leverage system topology or historical incident data (e.g., relationships from AppDynamics) to train or define this model. | Observability data available (metrics, events); Application topology or historical incident data prepared. | Suspect ranking model code and initial version that can output ranked probable causes given an anomaly. | High | Data Scientist / ML Engineer
Develop Future Prediction Model | Create a predictive model to forecast future performance issues or capacity needs based on trends in the metrics. Use time-series forecasting on metric data (e.g., Prometheus) to predict anomalies or threshold breaches before they occur. | Historical metrics data aggregated (from Prometheus); Central data store available for training. | Future prediction model code and initial trained model for forecasting potential issues. | Medium | Data Scientist / ML Engineer
Implement Model Training Pipeline (Dagster) | Using Dagster, implement pipeline jobs that orchestrate training for the anomaly detection, suspect ranking, and prediction models. The pipeline should fetch training data, execute model training (possibly dispatching to Celery workers), validate model performance, and save updated models to the model store. | Dagster set up; ML model code for anomaly/suspect/prediction available; Data pipeline in place for training data. | Automated training pipeline (Dagster job) that can be run on-demand or on schedule to retrain models with new data. | High | ML Engineer / Data Engineer
Implement Celery Training Tasks | Develop Celery task functions for training each ML model (anomaly detection, suspect ranking, future prediction). Ensure these tasks load the relevant data, train the model using the latest code, and save the model artifact and metrics, running asynchronously when triggered. | Celery set up; ML model code developed for each model; Access to data and model storage. | Asynchronous training task implementations (Celery tasks) for each model, integrated with the pipeline/orchestrator. | High | ML Engineer / Backend Engineer
Implement MCP Job Scheduler (Dagster) | Configure scheduled jobs (using Dagster schedules/sensors or external triggers) that periodically run the model training and analysis pipelines. The MCP scheduler coordinates regular retraining (e.g., nightly or weekly) and possibly periodic anomaly detection runs, ensuring the system’s models and analyses stay up-to-date. | Model training pipeline implemented; Celery tasks in place for execution. | MCP (job scheduling) configured – e.g., Dagster schedules that automatically trigger model retraining and data analysis at defined intervals. | Medium | ML Engineer / SRE
Set Up Model Store (Artifact Repo) | Establish a repository for storing trained model artifacts. This could involve setting up an artifact storage service or file store (e.g., S3 bucket or on-prem storage) where versioned models for anomaly detection, suspect ranking, and prediction can be saved and retrieved. | Infrastructure ready; Requirements from model pipeline on storage format/location determined. | Model store configured and accessible (with appropriate directories/buckets), and code is able to save/load models from it. | Medium | DevOps Engineer / ML Engineer
Set Up Metadata Database | Deploy a metadata database to track model metadata and system events. Define schema/tables for information such as model versions, training metrics, anomaly detection results, and agent action logs to ensure traceability and auditability of the system’s decisions. | Infrastructure ready; Data points to track identified during pipeline and agent design. | Running metadata database (e.g., PostgreSQL) with schemas for model info and observability events, accessible by the system for read/write. | Medium | Backend Engineer / DevOps Engineer
LangChain Orchestrator Framework Setup | Set up the LangChain framework to handle the multi-agent orchestration logic. Initialize the agent environment, define any initial prompt templates or memory structures, and prepare the system to coordinate multiple AI agents (ensuring they can share context or pass results as needed). | Architecture & design finalized (knowledge of required agents and tools); Base environment ready for installing LangChain and dependencies. | LangChain orchestrator initialized in code, ready to host multiple agents and manage their interactions (initial configuration complete). | High | AI Engineer / Backend Engineer
Develop FastAPI Router Service | Implement a FastAPI service that serves as the API layer and request router for the system. Define endpoints (e.g., /query, /action, /train) that receive requests from the UI or other sources and route them to the appropriate agent or pipeline (via the LangChain orchestrator) for processing. | LangChain orchestrator in place (to call into); Infrastructure ready for running API service. | FastAPI application running with defined endpoints for chatbot queries and system triggers, connected to the orchestrator logic. | High | Backend Engineer
Integrate LLM Executor (Language Model) | Integrate a Large Language Model (LLM) into the system (via API or SDK) to handle natural language understanding and generation for the chatbot and agents. Configure the LLM client (e.g., Gemini API) and ensure the orchestrator can invoke it to interpret user queries and generate responses or analyze unstructured data (like logs). | Orchestrator framework ready; LLM provider selected and access (API key or model) available. | LLM integrated (with credentials/config) and tested to ensure it can be called for generating responses within agent workflows. | High | AI Engineer / Backend Engineer
Implement Agent Selector Logic | Develop the logic to choose appropriate agent(s) based on the input query or situation. For example, determine when to invoke the anomaly detection agent vs. the log analysis agent vs. multiple agents in sequence. This could be rule-based or use the LLM to classify the query type, ensuring the system engages the right components for each request. | Orchestrator framework in place; Defined set of agents and their capabilities known. | Agent selection module integrated into the orchestrator, which directs incoming requests to the relevant agent or workflow automatically. | Medium | AI Engineer / Backend Engineer
Implement Prompt Validator | Create a component to validate and sanitize user prompts/commands before processing. This ensures security and reliability (e.g., removing any SQL injection attempts in queries, filtering out unsupported requests) and can also format or enrich the prompt to match the expected input format for the agents. | FastAPI service and orchestrator input pipeline established (to hook into); Security requirements defined. | Prompt validation module in place, with all incoming queries being checked/cleaned, improving system robustness and security. | Medium | Backend Engineer / Security Engineer
Develop Anomaly Detection Agent | Implement the anomaly detection agent that uses the trained anomaly detection model to analyze metrics in real-time or on-demand. Integrate this agent into the orchestrator so it can be invoked via a request or automatically. It should fetch current metric data (from Prometheus/AppDynamics) and return any detected anomalies with context. | Anomaly detection model available; Prometheus/AppDynamics data accessible; Orchestrator framework ready to integrate agent. | Anomaly Detection agent component implemented and registered with orchestrator, capable of returning anomaly insights when called. | High | AI Engineer / ML Engineer
Develop Suspect Ranking Agent | Implement the suspect ranking agent that, given an identified anomaly or incident, uses the suspect ranking model and system data to determine likely root causes. The agent should gather necessary context (recent anomalies, service dependencies) and produce an ordered list of suspect components or issues. Integrate this into the orchestrator workflow (often to be called after anomaly detection). | Suspect ranking model available; Anomaly detection results accessible (or anomaly agent implemented); Orchestrator ready for agent integration. | Suspect Ranking agent implemented and integrated, providing root cause analysis (ranked suspects) when invoked with an anomaly context. | High | AI Engineer / ML Engineer
Develop Future Prediction Agent | Implement the future prediction agent using the trained forecasting model. This agent can respond to queries about potential future issues or proactively analyze trends. When invoked, it should fetch recent metric trends and apply the prediction model to highlight any upcoming risks (e.g., capacity saturation). Integrate it into the orchestrator for on-demand use. | Future prediction model available; Relevant metric data accessible; Orchestrator ready for agent integration. | Future Prediction agent implemented, integrated into orchestrator, capable of providing forecasts or early warnings when triggered. | Medium | AI Engineer / ML Engineer
Develop Log Analysis Agent | Implement a log analysis agent that can query and analyze logs for troubleshooting. Using the Splunk integration, this agent retrieves log entries relevant to a given timeframe or issue and can use the LLM to parse and summarize log patterns or errors. Integrate it such that it can be invoked to provide insights from logs (for example, when investigating an anomaly). | Splunk log integration in place; LLM integrated for language understanding; Orchestrator framework ready. | Log Analysis agent implemented and integrated, capable of retrieving relevant logs and summarizing findings as part of the multi-agent workflow. | High | AI Engineer / SRE
Develop Automation Agent | Implement an automation agent capable of executing predefined remedial actions or adjustments in the environment. For instance, it can use OpenShift API calls to scale up/down services, restart pods, or run scripts when directed. Integrate this agent to be triggered either by user command or automatically (after certain analyses), including safety checks for any action. | OpenShift API integration complete; Predefined action scripts/runbooks available; Orchestrator ready for agent integration. | Automation agent implemented, integrated with orchestrator, capable of performing environment changes (with appropriate safeguards) upon request. | Medium | SRE / DevOps Engineer
Develop Alerting Agent | Implement an alerting agent responsible for sending notifications of critical detected issues. This agent monitors outputs from anomaly detection (and other agents) and generates alerts via channels like email or chat. It can utilize the LLM to craft clear summary messages of the situation. Integrate it to automatically trigger when high-priority anomalies or conditions are observed. | Anomaly detection agent in place (to provide triggers); Notification channels set up (e.g., SMTP or chat API credentials); Orchestrator or scheduling to run checks. | Alerting agent implemented that can send out notifications with summary of issues, integrated with the system’s detection mechanisms. | Medium | SRE / DevOps Engineer
UI/UX Design for Chatbot Interface (MCP Chatbot) | Design the user interface and experience for the observability chatbot (MCP Chatbot). Create wireframes or mockups to define how users will interact with the chatbot, including the chat dialog layout, ways to display metrics or charts in responses, and overall visual style for the dashboard elements. | System requirements and use-cases defined (from architecture planning); Feedback from SRE/users on desired UI features. | Complete set of UI/UX design mockups and specifications for the chatbot interface and associated dashboard elements. | Medium | UI/UX Designer
Implement Chatbot UI Frontend | Develop the frontend application for the chatbot interface as per the design. This may be a web-based UI (or integrated into a chat platform) where users can input queries and view rich responses (text, charts, links). Build interactive components (chat input box, response list, etc.) and apply styling. | UI design finalized; Basic backend API endpoints available for testing (FastAPI service). | Functional chatbot UI application that allows users to converse with the MCP Chatbot and displays results in an intuitive format. | High | Frontend Developer
Integrate UI with Backend Services | Connect the chatbot UI to the backend FastAPI service and orchestrator. Implement API calls (REST or WebSockets) from the frontend to send user questions to the backend, and update the UI with the returned answers or alerts. Ensure real-time interaction is smooth and handle loading states or errors on the UI side. | Chatbot UI frontend built; FastAPI router and agent backend endpoints operational. | End-to-end user interaction flow working: queries from UI reach the backend, and responses from agents are shown in the UI. UI and backend operate seamlessly together. | High | Frontend Developer / Backend Engineer
End-to-End Integration Testing | Test the entire system workflow with realistic scenarios. Verify that data flows from sources through the pipeline to the models correctly, that each agent produces the expected output, and that the orchestrator coordinates them properly for various use cases (an anomaly occurs, user asks a question, etc.). Fix any issues in data handoff or agent coordination uncovered during testing. | All components implemented (data integration, models, agents, orchestrator, UI). | Validated system behavior across all components; list of bugs and issues resolved to ensure end-to-end functionality meets requirements. | High | QA Engineer / Whole Team
Performance & Load Testing | Evaluate how the system performs under heavy load and data volumes. Simulate high frequency of incoming data (metrics/logs) and multiple concurrent user queries to test system scalability. Monitor response times, system resource usage, and model execution times. Optimize any performance bottlenecks and adjust system scaling (e.g., number of Celery workers or API instances). | System integrated and stable (after integration testing); Test environment with large data volume ready. | Performance test report detailing system capacity, throughput, and any identified bottlenecks, with adjustments made (tuning or scaling guidelines) to meet performance targets. | Medium | SRE / QA Engineer
Security Audit & Hardening | Conduct a thorough security review of the system. Validate that data access is secure (credentials are protected, connections are encrypted), and that the system is resilient to common threats (e.g., injection attacks via the chatbot, DDoS on the API). Implement enhancements such as tightening access controls, adding authentication/authorization to the UI and API, and ensuring compliance requirements (like audit logs in the metadata DB) are met. | Core system functionality in place; (Preferably after integration, so the full attack surface is known). | Security assessment report and completed hardening tasks (secure configurations, authentication enabled, etc.), resulting in a robust, secure system ready for production. | Medium | Security Engineer / DevOps Engineer
User Acceptance Testing (UAT) | Have end-users (SREs/DevOps team) test the system in a staging environment. Gather feedback on the chatbot responses, usefulness of recommendations, and UI/UX. Verify that the system meets all acceptance criteria and refine any aspects (fine-tune model thresholds, UI adjustments, etc.) based on real user interaction before final launch. | System fully implemented and deployed to a test/staging environment; Basic documentation available for users. | Approval from users that the system is effective and ready, along with any final change requests addressed to ensure the system meets operational needs. | Medium | End Users (SRE team) / QA
Documentation & Knowledge Transfer | Prepare comprehensive documentation for the entire system. This includes architecture diagrams, component descriptions, operational runbooks, and user guides for the chatbot and automation features. Also, conduct training or handover sessions with the operations team to ensure they can maintain and extend the system as needed. | System features finalized (after incorporating UAT feedback); Input from all developers on their components. | Complete documentation repository (wiki or manuals) and successful knowledge transfer sessions, enabling the team to support the system post-deployment. | Medium | Technical Writer / Team Lead (with input from Team)
Production Deployment & Monitoring Setup | Deploy the observability system to the production environment. Ensure all services (data collectors, pipelines, orchestrator API, UI, etc.) are running with proper configuration. Set up monitoring for the system itself (dashboards and alerts for the health of the new observability platform, e.g., agent errors, latency, etc.) to ensure reliability. Finalize backup and recovery plans for the new components. | Successful UAT sign-off; Security and performance issues resolved; Documentation available for ops. | Live production deployment of the Agentic Observability system, and a monitoring dashboard/alerts for the system’s own health, indicating readiness for full use. | High | DevOps Engineer / SRE